## QA Summary
TableMates QA Test Tracker
Use this workbook to record user, admin, and integration testing before submission.
Section | Owner | Progress | Notes | Demo Accounts | Password | Restaurant
User Flow | Frontend QA | 3/17 |  | bellaadmin@tablemates.com | admin123 | Bella Italia
Admin Flow | Frontend QA | 0/18 |  | sushiadmin@tablemates.com | admin123 | Sushi House
Integration | Joint QA | 3/6 |  | burgeradmin@tablemates.com | admin123 | Burger Corner
|  |  |  | goldenadmin@tablemates.com | admin123 | Golden Fork
Execution Notes |  |  |  | Status Legend
1 | Run backend from project root using npm run dev |  |  | Not Run | Not tested yet
2 | Run frontend from client using npm run dev |  |  | Pass | Worked as expected
3 | Open http://localhost:5173 for UI testing |  |  | Fail | Needs bug fix
4 | Use demo mode accounts listed on the right |  |  | Blocked | Cannot test due to dependency or issue
5 | Record Pass, Fail, or Blocked in each test case row

## User Flow
User Flow Test Cases
Customer-facing functionality and validations.
TC ID | Test Case | Steps | Expected Result | Priority | Status | Actual Result | Comments
U-01 | View homepage | Open http://localhost:5173 | Homepage loads with restaurant list | High | Pass
U-02 | User signup success | Go to Sign Up, enter valid email/password/confirm password, submit | Account is created successfully | High | Pass
U-03 | User signup with empty fields | Leave one or more signup fields empty, submit | Validation message is shown | Medium | Pass
U-04 | User signup with short password | Enter a password under required length | Validation message is shown | Medium | Fail
U-05 | User signup with mismatched passwords | Enter different password and confirm password | Validation message is shown | Medium | Not Run
U-06 | User login success | Go to Login, enter valid customer credentials, submit | User is redirected to user dashboard | High | Not Run
U-07 | User login with wrong credentials | Enter wrong email or password | Error message is shown | High | Not Run
U-08 | Access protected user page without login | Open reservation or user page directly without login | User is redirected to login | High | Not Run
U-09 | Search restaurant | Type restaurant name, location, or cuisine in search | Matching restaurants are filtered correctly | Medium | Not Run
U-10 | Open reservation page | Click View Tables on a restaurant | Reservation page opens with correct restaurant selected | High | Not Run
U-11 | Show only available tables | Open reservation page for a restaurant | Only available tables appear in dropdown | High | Not Run
U-12 | Reservation validation empty fields | Leave one or more reservation fields empty and submit | Validation error is shown | High | Not Run
U-13 | Reservation invalid guest count | Enter guest count as 0 or invalid number | Validation error is shown | High | Not Run
U-14 | Successful reservation | Select available table, fill details, submit | Reservation confirmation page appears | High | Not Run
U-15 | Reservation confirmation details | Complete reservation | Confirmation page shows correct restaurant, table, date, time, and guests | Medium | Not Run
U-16 | Book already reserved table | Try to reserve a table that is already reserved | Booking is blocked or table is unavailable | High | Not Run
U-17 | Logout user | Click logout from user dashboard | User session is cleared and returns to public page | Medium | Not Run

## Admin Flow
Admin Flow Test Cases
Restaurant admin login, reservations, and table management.
TC ID | Test Case | Steps | Expected Result | Priority | Status | Actual Result | Comments
A-01 | Admin login success | Open admin login, enter valid admin email and password | Admin dashboard opens | High | Not Run
A-02 | Admin login invalid credentials | Enter wrong admin credentials | Error message is shown | High | Not Run
A-03 | Admin login with non-admin account | Try logging in with customer account | Access is denied with message | High | Not Run
A-04 | View own restaurant dashboard | Login as one admin | Only that restaurant's data is shown | High | Not Run
A-05 | Login as another restaurant admin | Login using another demo admin account | Correct restaurant dashboard is shown | High | Not Run
A-06 | View reservations list | Open admin dashboard | Reservation list loads correctly | High | Not Run
A-07 | Reservation appears after customer booking | Make reservation as customer, then open admin dashboard | New reservation appears in admin dashboard | High | Not Run
A-08 | Edit reservation | Click edit on reservation, change values, save | Reservation updates successfully | Medium | Not Run
A-09 | Delete reservation | Delete a reservation | Reservation is removed from dashboard | High | Not Run
A-10 | Table becomes available after reservation deletion | Delete reservation linked to reserved table | Table status changes back to available | High | Not Run
A-11 | View restaurant tables | Open Manage Tables | Only that restaurant's tables are shown | High | Not Run
A-12 | Add new table success | Add a table with unique table number | Table is created successfully | High | Not Run
A-13 | Add duplicate table number | Add another table with same table number in same restaurant | Validation error is shown | High | Not Run
A-14 | Edit table success | Edit table details and save | Updated table data is shown | Medium | Not Run
A-15 | Edit table to duplicate number | Change table number to one already existing in same restaurant | Validation error is shown | High | Not Run
A-16 | Delete table | Delete an existing table | Table is removed successfully | Medium | Not Run
A-17 | Booked table changes to reserved | Customer books available table | Admin table view updates table status to Reserved | High | Not Run
A-18 | Admin logout | Click logout | Admin session is cleared and redirected to admin login | Medium | Not Run

## Integration
Integration Test Cases
Cross-flow behavior between customer and admin sides.
TC ID | Test Case | Steps | Expected Result | Priority | Status | Actual Result | Comments
I-01 | Customer booking reflected in admin dashboard | Customer books table, admin checks dashboard | Reservation appears correctly | High | Blocked
I-02 | Customer booking reflected in table status | Customer books table, admin checks manage tables | Table status changes to Reserved | High | Pass
I-03 | Deleted reservation releases table | Admin deletes reservation | Related table becomes Available again | High | Pass
I-04 | Restaurant separation | Login as different admins | Each admin sees only their own restaurant data | High | Blocked
I-05 | Page stability | Navigate through user and admin pages | No crashes or blank screens | High | Pass
I-06 | Validation messages | Trigger invalid form cases | Clear error messages are shown | Medium | Blocked